## Instructions
FRM-3176 Instructions
# | Risk Register
1 | Enter the project title, estimated cost, and start/end dates (project duration is automatically calculated) in the top left hand section (cells C2-5, D4) . For non-projects (organizations, processes), title is the organization title and the remaining fields are not required.
2 | Enter core risk description information in the dark blue section (Risk Description) of the worksheet.
3 | Select the PRE-HANDLING probability, cost and schedule impact in the red section (Pre-Handling Risk Analysis) to determine the % impact and calculate the MIN-MOST-MAX values. The frequency column is optional. Pre-Handling risk score is automatically calculated.
4 | Select a risk handling strategy (primary), enter the handling strategies you will use to employ the risk handling strategy, and the cost and schedule days to perform/implement the handling strategy in the dark grey section (Risk Handling).
5 | Select the POST-HANDLING probability, cost impact, and schedule impact in the light blue section (Post-Handling) to determine the % impact and calculate the MIN-MOST-MAX values. The frequency column is optional. Pre-Handling risk score is automatically calculated.
6 | Enter the date the risk was last reviewed and any additional comments and/or evaluation during the last risk review in the light grey section (Risk Review).
7 | If you have questions about risks, the form, or how to enter data into the form, please contact the ERM Team at Risk Management - Internal (RiskManagement1@nnss.onmicrosoft.com)
Risk Handling Responses
1 | Select the risk using the drop-down
2 | Enter a risk action (can have multiple actions assigned to a risk)
3 | Enter associated data (responsible person, status, due date, last reviewed date, and completion date and any other information)
4 | Review risk actions regularly
General
1 | Click on the header column cell to obtain additional pop-up instructions for each column.
2 | Use the grouping functions (+/-) at the top of the columns to expand/contract specific sections when working on the worksheet and/or printing the worksheet
3 | A reference column is included and colored the same color as the section - no user input or data is required for this column
4 | Columns in gray are automatically calculated or determined and do not require any direct user input (just input in the cells that the gray columns use)
Printing
1 | Expand or contract the columns that you want to be printed (only visible columns will be printed)
2 | Hide any blank rows with no data to avoid printing blank rows or extra pages
3 | Print on 11 x 17 paper and/or to pdf

## Risk Register
Common Project Risks Risk Register | [15 empty] | Common Project Risks Risk Register
Project (Or Organization/Process) Title |  | Common Project Risks
Project Budget
Project Start/Finish Dates |  | 2025-11-01
Total Project Duration (Calendar Days) |  | 0
Risk Description | [15 empty] | Pre-Handling Risk Analysis | [15 empty] | Risk Handling |  |  |  |  | Post-Handling | [15 empty] | Risk Review
Risk # | Title | Status | Risk Type | Risk Owner | Integrator | Project Phase | SME | IF | THEN | Risk Statement (Combined) | Trigger Event | Reserve Type | WBS | Activity ID | CORE RISK DATA | Probability | Probability Midpoint | Cost Impact (Percentage of Total Project Budget) | Cost Impact % Midpoint | MIN Cost Impact | Most Likely Cost Impact | MAX Cost Impact | Schedule Impact (Percentage of Total Project Duration) | Schedule Impact % Midpoint | MIN Sch Impact (Days) | MOST Likely Sch Impact (Days) | MAX Sch Impact (Days) | Frequency | Overall Impact Category | Risk Score | Pre-Handling Risk Analysis | Handling Strategy | Handling Actions | Handling Plan Cost | Handling Plan Schedule Impact (Days) | Risk Handling Strategies | Target Probability | Target Probability Midpoint | Target Cost Impact (Percentage of Total Project Budget) | Target Cost Impact % Midpoint | MIN Target Cost Impact - Post | MOST Likely Target Cost Impact - Post | MAX Target Cost Impact | Target Schedule Impact (Percentage of Total Project Duration) | Target Schedule Impact % Midpoint | MIN Target Schedule Impact (Days) | MOST Likely Target Schedule Impact (Days) | MAX Target Schedule Impact (Days) | Frequency Post | Overall Impact Category Post | Target Risk Score | Post Handling | Last Reviewed Date | Comments (Review)
1 | Resource availability | Draft | Threat | Project Mgr. |  | Construction |  | IF experienced and/or trained/qualified resources are not available to perform project tasks (from support organization - Engineering, Procurement, QA, ES&H, etc.) | THEN, key project activities may not be completed and/or documents/deliverable may have quality or completeness issues. | IF experienced and/or trained/qualified resources are not available to perform project tasks (from support organization - Engineering, Procurement, QA, ES&H, etc.), THEN, key project activities may not be completed and/or documents/deliverable may have quality or completeness issues. | [5 empty] | Likely (30%-70%) | 50% | [7 empty] | - | - | - | 4 |  | 0.15 |  | Avoid | Forecast upcoming work activities and communicate resource needs with support organizations. Provide realistic timeframes for documents and technical deliverables. Identify experience/expertise and utilize subcontract task orders if needed. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.06
2 | MSTS Logistical Issues Impact Subcontractor | Draft | Threat | SUB |  | Construction |  | IF logistics issues are encountered by MSTS supporting the subcontractor | THEN the subcontractor may experience delays or downtime costing the project additional cost | IF logistics issues are encountered by MSTS supporting the subcontractor, THEN the subcontractor may experience delays or downtime costing the project additional cost | [5 empty] | Likely (30%-70%) | 50% | [7 empty] | - | - | - | 4 |  | 0.12 |  | Accept | Ensure resources and equipment are available and setup subcontractor standby cost rate for any impacts. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.02
3 | Technical requirements definition | Draft | Threat | Project Mgr |  | Construction |  | IF preliminary / conceptual technical project requirements are significantly different than the final scope and requirements | THEN project costs will be variable and have a significant amount of uncertainty and schedule delays will occur | IF preliminary / conceptual technical project requirements are significantly different than the final scope and requirements, THEN project costs will be variable and have a significant amount of uncertainty and schedule delays will occur | [5 empty] | Likely (30%-70%) | 50% | [7 empty] | - | - | - | 4 |  | 0.42 |  | Mitigate | Work with customer to define requirements and communicate key decision points and impacts. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.2
4 | Customer and MSTS project planning processes do not align | Draft | Threat | PPD |  | Construction |  | IF MSTS does not have the needed technical requirements and decisions from the customer to met current project planning processes | THEN, project schedules can be delayed, cost estimates may not be accurate or variable, and/or significant risk acceptance maybe required, | IF MSTS does not have the needed technical requirements and decisions from the customer to met current project planning processes, THEN, project schedules can be delayed, cost estimates may not be accurate or variable, and/or significant risk acceptance maybe required, | [5 empty] | Highly Likely (70%-90%) | 80% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.49 |  | Mitigate | Define boundaries, communicate decisions and impacts, provide unit rates for costs where requirements can vary |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.3
5 | Technical Support | Draft | Threat | Project Mgr. |  | Construction |  | IF dedicated technical resources (e.g. design, procurement, etc.) are not available to award the subcontract, | THEN the project may not complete specific activities or deliverables on schedule leading to schedule delays and cost impacts. | IF dedicated technical resources (e.g. design, procurement, etc.) are not available to award the subcontract,, THEN the project may not complete specific activities or deliverables on schedule leading to schedule delays and cost impacts. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.3 |  | Mitigate | Utilize subcontract agreements and task orders. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.06
6 | Priority Level | Draft | Threat | PPD |  | Construction |  | IF projects with higher or competing priorities occur concurrently with this project and require the same resources | THEN the resources may not be available to support the project schedule, resulting in cost impacts and schedule delays. | IF projects with higher or competing priorities occur concurrently with this project and require the same resources, THEN the resources may not be available to support the project schedule, resulting in cost impacts and schedule delays. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.36 |  | Avoid | Work with execution and support organizations to prioritize work in advance. Obtain subcontract resources when necessary. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.08
7 | Stakeholder expectations | Draft | Threat | Project Mgr. |  | Construction |  | IF stakeholders do not accept or are not satisfied with planned values, scope, and locations | THEN scope, cost, and schedule delays may occur until concerns are resolved or additional risk acceptance may be required. | IF stakeholders do not accept or are not satisfied with planned values, scope, and locations, THEN scope, cost, and schedule delays may occur until concerns are resolved or additional risk acceptance may be required. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.24 |  | Transfer | Frequent meetings with customer. Decision log. Signed and approved SOW. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.12
8 | Long Lead Items | Draft | Threat | Project Mgr. |  | Construction |  | IF long lead materials are not available as scheduled | THEN work may be impacted causing schedule delays and cost impacts. | IF long lead materials are not available as scheduled, THEN work may be impacted causing schedule delays and cost impacts. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.36 |  | Mitigate | Document in assumptions, building schedule float, pre-ordering of long-lead items. Regular communication with Procurement. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.12
9 | Scope Creep | Draft | Threat | Project Mgr. |  | Construction |  | IF project scope changes during design, development, or construction | THEN scope, cost, and schedule impacts and delays will occur. | IF project scope changes during design, development, or construction, THEN scope, cost, and schedule impacts and delays will occur. | [5 empty] | Highly Likely (70%-90%) | 80% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.56 |  | Mitigate | Document assumptions and BOE. Remain agile. Perform BCRs as needed. Constant communication with customer and program. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.3
10 | Support Resources Ability to meet Commitments | Draft | Threat | Project Mgr. |  | Construction |  | IF support organizations (engineering, ES&H, etc.) are unable to meet document reviews and input schedule requirements | THEN, project schedule delays may occur for specific activities or deliverables. | IF support organizations (engineering, ES&H, etc.) are unable to meet document reviews and input schedule requirements, THEN, project schedule delays may occur for specific activities or deliverables. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.36 |  | Avoid | Provide early requests for support to support organizations. Early engagement. Continuous communication. Track design request progress. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.16
11 | Material Cost Increases and/or Availability | Draft | Threat | Project Mgr. |  | Construction |  | IF materials costs surge due to increased demand or other market conditions OR material availability is low | THEN increased materials costs or material delivery schedule will be adversely impacted. | IF materials costs surge due to increased demand or other market conditions OR material availability is low, THEN increased materials costs or material delivery schedule will be adversely impacted. | [5 empty] | Highly Likely (70%-90%) | 80% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.42 |  | Accept | Provide management reserve. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.12
12 | Weather | Draft | Threat | Project Mgr. |  | Construction |  | IF inclement weather requires a work delay or stoppage above and beyond anticipate delays in the BOE/assumptions and schedule | THEN the project activities will be delayed impacting the project schedule. | IF inclement weather requires a work delay or stoppage above and beyond anticipate delays in the BOE/assumptions and schedule, THEN the project activities will be delayed impacting the project schedule. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.09 |  | Accept | Build in schedule float and assumptions. View weather forecasts from the National Weather Service or equivalent and share with the IPT. Follow company requirements when adverse weather conditions are encountered. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.09
13 | Commissioning | Draft | Threat | Project Mgr. |  | Construction |  | IF commissioning fails or acceptance testing is not successfully completed | THEN additional/re-work will be required. | IF commissioning fails or acceptance testing is not successfully completed, THEN additional/re-work will be required. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.18 |  | Avoid | Detailed scope definitions and final designs. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.04
14 | Unanticipated Site Conditions Encountered | Draft | Threat | Project Mgr. |  | Construction |  | If unanticipated site conditions are discovered during the project work activities (e.g. radiological contamination, hazardous materials, historical sites, unanticipated utilities) | THEN work activities / project schedule may be delayed and cost impacts realized. | If unanticipated site conditions are discovered during the project work activities (e.g. radiological contamination, hazardous materials, historical sites, unanticipated utilities), THEN work activities / project schedule may be delayed and cost impacts realized. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.2 |  | Mitigate | Conduct site surveys and build into management reserve. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.06
15 | Equipment Availability | Draft | Threat | Construction Supervisor |  | Construction |  | If tools and/or equipment (heavy equipment, vehicles, tools, machines) are not available for use for activities in the project schedule | THEN work activities productivity and schedule will be adversely impacted causing delays and additional costs | If tools and/or equipment (heavy equipment, vehicles, tools, machines) are not available for use for activities in the project schedule, THEN work activities productivity and schedule will be adversely impacted causing delays and additional costs | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.2 |  | Mitigate | Identify equipment needs in WBS, CWP, and RLTB. Have multiple sources/vendors available or purchase or rent equipment. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.04
16 | Uncovering buried object during excavation | Draft | Threat | Project Mgr. |  | Construction |  | IF an object is uncovered during excavation | THEN excavation may pause or stop while the area or object is surveyed and evaluated impacting operations or construction | IF an object is uncovered during excavation, THEN excavation may pause or stop while the area or object is surveyed and evaluated impacting operations or construction | [5 empty] | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.1 |  | Mitigate | Perform GPR surveys of areas. Conduct historical research on drawings and utilities. Have a plan in place in an ALWCD to handle this occurrence as a normal part of operations to avoid work pauses or shutdowns. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.04
17 | Security Requirements | Draft | Threat | Project Mgr. |  | Construction |  | IF security requirements (escort) are not known | THEN security incidents and/or violations may occur and/or uncleared workers may not be able to work in the area. | IF security requirements (escort) are not known, THEN security incidents and/or violations may occur and/or uncleared workers may not be able to work in the area. | [5 empty] | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.04 |  | Avoid | Contact Security to determine security requirements and obtain escorts if required. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.02
18 | Equipment or Instrument Breakdowns | Draft | Threat | Project Mgr. |  | Construction |  | IF equipment or instrumentation breakdown | THEN work that requires this equipment may stop and affect project schedule. | IF equipment or instrumentation breakdown, THEN work that requires this equipment may stop and affect project schedule. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 5 |  | 0.18 |  | Mitigate | Have additional or back-up equipment or instruments available. Have technicians or mechanics on standby to troubleshoot and repair. Have an ALWCD to handle maintenance and repair of equipment. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 5 |  | 0.09
19 | NEPA Reviews | Draft | Threat | Project Mgr. |  | Construction |  | IF NEPA review identifies issues | THEN the project schedule can be adversely affected. | IF NEPA review identifies issues, THEN the project schedule can be adversely affected. | [5 empty] | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.1 |  | Mitigate | Early NEPA reviews to be performed during project initiation. Early scope definition. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.08
20 | Biological/Cultural Surveys Find Artifacts | Draft | Threat | Project Mgr. |  | Construction |  | IF the biological or cultural review has delays or finds artifacts | THEN the scope and schedule changes may be required during project execution causing cost and schedule modifications. | IF the biological or cultural review has delays or finds artifacts, THEN the scope and schedule changes may be required during project execution causing cost and schedule modifications. | [5 empty] | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.1 |  | Avoid | Perform biological/cultural surveys early in the project. Well-defined scope of work. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.06
21 | Wildlife Concerns | Draft | Threat | Project Mgr. |  | Construction |  | If discovery of a wildlife den or nest is located or nesting birds | Then pause work as required, notify the environmental and biological department | If discovery of a wildlife den or nest is located or nesting birds, Then pause work as required, notify the environmental and biological department | [5 empty] | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.16 |  | Avoid | Perform biological/cultural surveys early in the project. Close any wildlife access points prior to nesting season or winter months. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.08
22 | Funding Concerns | Draft | Threat | Program Manager |  | Construction |  | IF project funding is not available to meet project schedule | THEN the project schedule will be impacted. | IF project funding is not available to meet project schedule, THEN the project schedule will be impacted. | [5 empty] | Highly Likely (70%-90%) | 80% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.49 |  | Mitigate | Provide cost estimates and communicate impacts of not having funding to the customer. Work with Program to secure/commit needed project funding. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.35
23 | Roles and Responsibilities | Draft | Threat | Project Mgr. |  | Construction |  | IF roles and responsibilities are not clear or well understood | THEN there can be delays on decision-making and project schedule impacts. | IF roles and responsibilities are not clear or well understood, THEN there can be delays on decision-making and project schedule impacts. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 7 |  | 0.35 |  | Mitigate | Develop and document clear R&Rs for the project, including a RAM. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.09
24 | Cost Estimate Variability / Accuracy | Draft | Threat | Cost Estimating |  | Construction |  | IF the cost estimate is not accurate or the ramification of the range is not well-understood by the customer or management | THEN the project may not have sufficient funding to complete the project and/or significant reputational issues may occur impacting the project. | IF the cost estimate is not accurate or the ramification of the range is not well-understood by the customer or management, THEN the project may not have sufficient funding to complete the project and/or significant reputational issues may occur impacting the project. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 5 |  | 0.18 |  | Mitigate | Identify and communicate the class of estimate. Using estimating process to improve accuracy to definitive levels (Class II) prior to project baselining and funding authorization. Keep management reserve. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.15
25 | Design Review Quality | Draft | Threat | Engineering |  | Construction |  | IF design reviews are not adequate and do not identify functional or workability issues | THEN there will be construction delays and cost impacts to the project. | IF design reviews are not adequate and do not identify functional or workability issues, THEN there will be construction delays and cost impacts to the project. | [5 empty] | Highly Likely (70%-90%) | 80% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.35 |  | Mitigate | Communicate requests for engineering reviews. Ensure peer reviews are performed. Have a subcontractor engineering review if needed. Perform walkdowns and tabletops if necessary. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.16
26 | Non-Compliance | Draft | Threat | Project Mgr. |  | Construction |  | IF company and process requirements are not known or followed | THEN, the project risks being out of compliance which can result in legal, reputational, cost, or schedule issues and penalties. | IF company and process requirements are not known or followed, THEN, the project risks being out of compliance which can result in legal, reputational, cost, or schedule issues and penalties. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 5 |  | 0.25 |  | Mitigate | Understand/read company processes. Engage process owners/managers to better understand the process and impacts. Use experience resources and systems and tools that drive compliance. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.12
27 | ALWCD Development Time Not Accurate | Draft | Threat | Integrated Work Planning |  | Construction |  | IF ALWCD development time is not accurately budgeted for or scheduled for | THEN ALWCDs may not be approved in time and delay project activities and/or require work stoppages for ALWCD revisions and changes. | IF ALWCD development time is not accurately budgeted for or scheduled for, THEN ALWCDs may not be approved in time and delay project activities and/or require work stoppages for ALWCD revisions and changes. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.28 |  | Mitigate | Meet with IWP manager or organization planning manager during WBS development to determine work packages that are needed and the labor and time required to develop them prior to estimating. Include time/budget for work package changes and updates during the project. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.12
28 | Project Assumptions Not Captured or Documented | Draft | Threat | Project Mgr. |  | Construction |  | IF project assumptions are not captured, documented, or are missing | THEN impacts to cost and schedule may be significant if a situation is encountered or the estimate may not be accurate. | IF project assumptions are not captured, documented, or are missing, THEN impacts to cost and schedule may be significant if a situation is encountered or the estimate may not be accurate. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.25 |  | Mitigate | Work with technical SMEs and customer to capture a comprehensive list of assumptions. Use common project assumptions from other projects (lessons learned). |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.08
29 | Document Review and Approval Delays | Draft | Threat | Project Mgr. |  | Construction |  | IF documents / deliverables are not adequately developed, reviewed, and comments resolved in a timely manner | THEN, project schedule can be delayed and additional costs may be incurred. | IF documents / deliverables are not adequately developed, reviewed, and comments resolved in a timely manner, THEN, project schedule can be delayed and additional costs may be incurred. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 7 |  | 0.16 |  | Mitigate | Communicate review requests and due dates. Follow-up regularly as due dates draw closer. Use systems/tools to help manage reviews. Hold tabletop reviews with the team, prior to the due date, if necessary to capture their attention and time. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.12
30 | Pandemic Impacts | Draft | Threat | Project Mgr. |  | Construction |  | IF a pandemic is encountered during pre-construction or construction | THEN costs will increase and project schedule delays will occur. | IF a pandemic is encountered during pre-construction or construction, THEN costs will increase and project schedule delays will occur. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.12 |  | Accept | Adjust when/if it happens implementing ES&H provided protocols and requirements. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.04
31 | Connection to Site Infrastructure | Draft | Threat | Project Mgr. |  | Construction |  | If the project/facility being constructed needs to connect to site infrastructure or utilities | THEN final connection work may be impacted leading to cost impacts and schedule delays | If the project/facility being constructed needs to connect to site infrastructure or utilities, THEN final connection work may be impacted leading to cost impacts and schedule delays | [5 empty] | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.12 |  | Mitigate | Work to schedule the required outages in advance and on non-normal workdays to alleviate or reduce impacts. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.03
32 | SOW in RFP is Not Well-Defined | Draft | Threat | Project Mgr. |  | Construction |  | IF the SOW and requirements in the RFP (Exhibit B) are unclear or not well-defined | THEN subcontractor bids will be variable/inaccurate and/or the proposal process will be delayed. | IF the SOW and requirements in the RFP (Exhibit B) are unclear or not well-defined, THEN subcontractor bids will be variable/inaccurate and/or the proposal process will be delayed. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.24 |  | Mitigate | Hold formal reviews. Hold walkdowns or tabletops. Document SOW with formal acceptance or email documentation. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.08
33 | Changes in Labor Rates | Draft | Threat | Project Mgr. |  | Construction |  | IF there are changes in labor rates | THEN the cost estimate will be affected. | IF there are changes in labor rates, THEN the cost estimate will be affected. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.15 |  | Accept | Put it assumptions and management reserve for rate changes as they will occur 1-2 times a year and annually. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.12
34 | Standdown Occurs | Draft | Threat | Project Mgr. |  | Construction |  | IF facility operations or execution requires a standdown (outside what is accounted for in the project budget) | THEN project work activities can be delays and cost impacts can be realized. | IF facility operations or execution requires a standdown (outside what is accounted for in the project budget), THEN project work activities can be delays and cost impacts can be realized. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.18 |  | Accept | Normally standdowns are only for an hour or a day maximum. Work in schedule float to accommodate one per year/project. Have alternate work activities identified. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.04
35 | Late Comments | Draft | Threat | Project Mgr. |  | Construction |  | IF comments from reviewers and stakeholders are not received on time | THEN document / deliverable completion and quality will be affected requiring additional changes and revisions impacting cost and schedule. | IF comments from reviewers and stakeholders are not received on time, THEN document / deliverable completion and quality will be affected requiring additional changes and revisions impacting cost and schedule. | [5 empty] | Highly Likely (70%-90%) | 80% |  |  | - | - | - |  |  | - | - | - | 6 |  | 0.48 |  | Mitigate | Use systems/tools to manage document reviews. Use email reminders. Hold review sessions with technical SMEs and stakeholders when necessary. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.12
36 | Computer / Network Issues | Draft | Threat | Information Technology |  | Construction |  | IF project personnel cannot access their computers or the internet/intranet or network | THEN they will be unable to communicate, work on documents, or sign/approve them causing schedule delays and incurring additional costs. | IF project personnel cannot access their computers or the internet/intranet or network, THEN they will be unable to communicate, work on documents, or sign/approve them causing schedule delays and incurring additional costs. | [5 empty] | Highly Likely (70%-90%) | 80% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.56 |  | Mitigate | Have a backup connection (Wi-Fi or cellular) where possible. IT has personnel ready to address emerging issues. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.12
37 | Subcontractor Schedule Delays | Draft | Threat | Project Mgr. |  | Construction |  | IF the subcontractor does not complete work according to the schedule | MSTS oversight and support will incur additional costs and the project will experience schedule delays. | IF the subcontractor does not complete work according to the schedule, MSTS oversight and support will incur additional costs and the project will experience schedule delays. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.2 |  | Transfer | Provide incentives for subcontractors to finish early. Put sufficient time/float in project schedule to adjust for schedule delays. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.16
38 | Mission/ Project Activities Not Integrated | Draft | Threat | Project Mgr. |  | Construction |  | IF Mission activities, Facility Operations / Maintenance or Construction activities are not properly integrated | THEN a schedule impact will be realized and a day for day schedule slip will occur | IF Mission activities, Facility Operations / Maintenance or Construction activities are not properly integrated, THEN a schedule impact will be realized and a day for day schedule slip will occur | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.3 |  | Mitigate | PM will work with Mission, Facility, Construction and functional organizations to ensure activities are integrated and deconflicted. Coordinate with facility on work authorization and release (e.g. POD, POW). Anticipate any potential unplanned activities. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.09
39 | Facility Personnel Capacity Exceeded | Draft | Threat | Project Mgr. |  | Construction |  | IF project personnel required to perform scope exceed the maximum personnel capacity limits at the facility | THEN project work activities and/or operations may be impacted causing cost and schedule delays. | IF project personnel required to perform scope exceed the maximum personnel capacity limits at the facility, THEN project work activities and/or operations may be impacted causing cost and schedule delays. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.18 |  | Mitigate | Maintain communications with facility manager and/or facility access control to ensure onsite workers are within facility limits. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.04
40 | Project activities impact available ventilation | Draft | Threat | Project Mgr. |  | Construction |  | IF planned project activities impact the ventilation in the facility | THEN work may be impacted causing schedule delays and cost impacts. | IF planned project activities impact the ventilation in the facility, THEN work may be impacted causing schedule delays and cost impacts. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.18 |  | Mitigate | Work with the facility (PULSE-specific) to ensure adequate airflow is available for operations and project activities. Use temporary or additional ventilation. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.06
41 | Changes to Codes or Standards | Draft | Threat | Project Mgr. |  | Construction |  | IF there are changes to codes or standards (NFPA, NDEP/NEPA, ANSI) as documented in the project's code of record | THEN work may be impacted causing schedule delays and cost impacts. | IF there are changes to codes or standards (NFPA, NDEP/NEPA, ANSI) as documented in the project's code of record, THEN work may be impacted causing schedule delays and cost impacts. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.3 |  | Mitigate | Ensure any changes to codes or standards are known or anticipate prior to the start of detailed design, construction, or field activities. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.12
42 | Project Work Impacts Facility Utilities | Draft | Threat | Project Mgr. |  | Construction |  | IF project work inadvertently impacts operating systems (power, water, communication, etc.) | THEN project work activities and/or operations may be impacted causing cost and schedule delays. | IF project work inadvertently impacts operating systems (power, water, communication, etc.), THEN project work activities and/or operations may be impacted causing cost and schedule delays. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 4 |  | 0.35 |  | Mitigate | Work closely with facility management to evaluate impacts on utilities and systems prior to performing activity-level work. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.16
43 | Field Conditions Not Identified During Design | Draft | Threat | Project Mgr. |  | Construction |  | IF field conditions are not correctly captured during Design phase | THEN work may be impacted causing schedule delays and cost impacts. | IF field conditions are not correctly captured during Design phase, THEN work may be impacted causing schedule delays and cost impacts. | [5 empty] | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 5 |  | 0.35 |  | Mitigate | Perform walkdowns with technical personnel at the field location. |  |  |  | Likely (30%-70%) | 50% |  |  | - | - | - |  |  | - | - | - | 3 |  | 0.12
44 | Labor Disputes Impact Craft Availability | Draft | Threat | Project Mgr. |  | Construction |  | IF craft disputes impact or delay project or support activities | THEN work may be impacted causing schedule delays and cost impacts. | IF craft disputes impact or delay project or support activities , THEN work may be impacted causing schedule delays and cost impacts. | [5 empty] | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 2 |  | 0.16 |  | Mitigate | Develop mitigations plans when strikes are likely. |  |  |  | Low Likelihood (10%-30%) | 20% |  |  | - | - | - |  |  | - | - | - | 1 |  | 0.1
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -
[10 empty] | , | [9 empty] | - | - | - |  |  | - | - | - |  |  | - | [10 empty] | - | - | - |  |  | - | - | - |  |  | -

## Risk Handling Responses
Risk | Risk Action(s) | Responsible Person | Status | Reponse Type | Projected Due Date | Last Reviewed Date | Completion Date | Other Information
| Add risk action(s) | Name Here | On Track | Action | 2025-10-31 | 2025-10-25 | 2025-11-03

## Scoring
Scoring scheme
| NIL | Not Likely | Low Likelihood | Likely | Highly Likely | Near Certainty
Probability | NIL | <10% | 10%-30% | 30%-70% | 70%-90% | >90%
| NIL | Minimal | Minor | Moderate | Significant | Severe | Cost Impact Range | Midpoint % | Dollar Impact ($)
Cost (Percent of budget) | NIL | 0%-5% | 5%-10% | 10%-25% | 25%-40% | >40% | Minimal (0%-5%) | 0.025 | 0
Schedule | NIL | 0%-5% | 5%-10% | 10%-25% | 25%-40% | >40% | Minor (5%-10%) | 0.075 | 0
[7 empty] | Moderate (10%-25%) | 0.175 | 0
[7 empty] | Significant (25%-40%) | 0.325 | 0
Probability | Near Certainty | 5 | 13 | 20 | 22 | 25 | Severe (>40%) | 0.45 | 0
| Highly Likely | 4 | 12 | 15 | 21 | 24
| Likely | 3 | 8 | 14 | 17 | 23 | Schedule Impact Range | Midpoint % | Calendar Days Impact
| Low Likelihood | 2 | 7 | 10 | 16 | 19 | Minimal (0%-5%) | 0.025 | 0
| Not Likely | 1 | 6 | 9 | 11 | 12 | Minor (5%-10%) | 0.075 | 0
|  | Minimal | Minor | Moderate | Significant | Severe | Moderate (10%-25%) | 0.175 | 0
|  | Impact |  |  |  |  | Significant (25%-40%) | 0.325 | 0
[7 empty] | Severe (>40%) | 0.45 | 0

## Look Ups
Cost Impact Category |  | Schedule Impact Category |  |  | Minimal (0%-5%) | Minor (5%-10%) | Moderate (10%-25%) | Significant (25%-40%) | Severe (>40%) | Dropdown Text | Category Name
Minimal (0%-5%) |  | Minimal (0%-5%) |  | Near Certainty (>90%) | 5 | 13 | 20 | 22 | 25 | Minimal (0%-5%) | Minimal
Minor (5%-10%) |  | Minor (5%-10%) |  | Highly Likely (70%-90%) | 4 | 12 | 15 | 21 | 24 | Minor (5%-10%) | Minor
Moderate (10%-25%) |  | Moderate (10%-25%) |  | Likely (30%-70%) | 3 | 8 | 14 | 17 | 23 | Moderate (10%-25%) | Moderate
Significant (25%-40%) |  | Significant (25%-40%) |  | Low Likelihood (10%-30%) | 2 | 7 | 10 | 16 | 19 | Significant (25%-40%) | Significant
Severe (>40%) |  | Severe (>40%) |  | Not Likely (<10%) | 1 | 6 | 9 | 11 | 12 | Severe (>40%) | Severe
Probability Category | Risk Status Options |  | Project Phase |  | Management/Contingency Reserve |  | Handling Plan Strategy |  | Risk Type | Dropdown Text | Category Name | Definition
Not Likely (<10%) | Active |  | Construction |  | Management Reserve |  | Mitigate (T) |  | Threat | Not Likely (<10%) | Not Likely | Event expected to occur
Low Likelihood (10%-30%) | Handled |  | Design |  | Contingency Reserve |  | Accept (T) |  | Opportunity | Low Likelihood (10%-30%) | Low Likelihood | Event more likely than not to occur
Likely (30%-70%) | Draft |  | Commissioning |  |  |  | Avoid (T) |  |  | Likely (30%-70%) | Likely | Event may or may not occur
Highly Likely (70%-90%) | Closed - Expired |  | All |  |  |  | Transfer (T) |  |  | Highly Likely (70%-90%) | Highly Likely | Event less likely than not to occur
Near Certainty (>90%) | Closed - Realized |  | Undefined |  |  |  | Share (T) |  |  | Near Certainty (>90%) | Near Certainty | Event not expected to occur
| Excluded | [5 empty] | Enhance (O)
| Never Approved | [5 empty] | Exploit (O)
Ignore (O)
Share (O)
Undefined

## Lookup2
Actions
Complete / Control Implemented
Not Started
Proposed
On Track
Off Track
No Longer Required
Action
Control

## Sheet1 (hidden)
FRM - 3176 (Project Title) Risk Register
Risk Details | [54 empty] | Scoring Details | [162 empty] | Plan Details
Title | ID | Owner | Status | Category | Raised By | Interested Parties/Team | Phase | Risk Tier | Status | Stakeholder(s) | Type | Risk Statement IF | Description | Risk Statement THEN | Background -Do not use standard background field | Date Raised | Approval Date | Next Review | Comments | Last Comprehensive Review Note | Reviewed By | Last Comprehensive Review | Impact (Cost and Schedule) Basis | Feedback By | Last Feedback | Notes | Metric | Closure Criteria | Trigger Event | WBS | Activity ID(s) | Project Risk ID | Date Closed | Federal Acceptance Date | Custom Date 3 | Custom Date 4 | Integrator | ION POC | Custom Resource 3 | Custom Resource 4 | Potential Operational Upset | Priority | Management/Contingency Reserve | PEMP Goal(s) | Activity View | Plan Title | Group | Black Flag | Black Flag Comments | Scoring Scheme | Description | Trigger Event | Trigger Event Passed | Target Resolution | Category 1 | Units 1 | Category 2 | Units 2 | Category 3 | Units 3 | Category 4 | Units 4 | Category 5 | Units 5 | Category 6 | Units 6 | Category 7 | Units 7 | Category 8 | Units 8 | Category 9 | Units 9 | Category 10 | Units 10 | Category 11 | Units 11 | Category 12 | Units 12 | Current Exposure | Current Distribution | Current Probability (%) | Current Occurences | Current Years | Current Category 1 Min | Current Category 1 Expected | Current Category 1 Max | Current Category 2 Min | Current Category 2 Expected | Current Category 2 Max | Current Category 3 Min | Current Category 3 Expected | Current Category 3 Max | Current Category 4 Min | Current Category 4 Expected | Current Category 4 Max | Current Category 5 Min | Current Category 5 Expected | Current Category 5 Max | Current Category 6 Min | Current Category 6 Expected | Current Category 6 Max | Current Category 7 Min | Current Category 7 Expected | Current Category 7 Max | Current Category 8 Min | Current Category 8 Expected | Current Category 8 Max | Current Category 9 Min | Current Category 9 Expected | Current Category 9 Max | Current Category 10 Min | Current Category 10 Expected | Current Category 10 Max | Current Category 11 Min | Current Category 11 Expected | Current Category 11 Max | Current Category 12 Min | Current Category 12 Expected | Current Category 12 Max | Current Probability Band | Current Frequency Band | Current Category 1 Band | Current Category 2 Band | Current Category 3 Band | Current Category 4 Band | Current Category 5 Band | Current Category 6 Band | Current Category 7 Band | Current Category 8 Band | Current Category 9 Band | Current Category 10 Band | Current Category 11 Band | Current Category 12 Band | Target Exposure | Target Distribution | Target Probability (%) | Target Occurrences | Target Years | Target Category 1 Min | Target Category 1 Expected | Target Category 1 Max | Target Category 2 Min | Target Category 2 Expected | Target Category 2 Max | Target Category 3 Min | Target Category 3 Expected | Target Category 3 Max | Target Category 4 Min | Target Category 4 Expected | Target Category 4 Max | Target Category 5 Min | Target Category 5 Expected | Target Category 5 Max | Target Category 6 Min | Target Category 6Expected | Target Category 6 Max | Target Category 7 Min | Target Category 7 Expected | Target Category 7 Max | Target Category 8 Min | Target Category 8 Expected | Target Category 8 Max | Target Category 9 Min | Target Category 9 Expected | Target Category 9 Max | Target Category 10 Min | Target Category 10 Expected | Target Category 10 Max | Target Category 11 Min | Target Category 11 Expected | Target Category 11 Max | Target Category 12 Min | Target Category 12 Expected | Target Category 12 Max | Target Probability Band | Target Frequency Band | Target Category 1 Band | Target Category 2 Band | Target Category 3 Band | Target Category 4 Band | Target Category 5 Band | Target Category 6 Band | Target Category 7 Band | Target Category 8 Band | Target Category 9 Band | Target Category 10 Band | Target Category 11 Band | Target Category 12 Band | Date Realized | Actual Cost | Current MCV | Current EMV | Current Risk Level (Score) | Current Risk Level (Band) | Weight Type | Current Weight Band | Current Weighted Score | Current Driving Impact Category | Current Driving Impact Level | Target MCV | Target EMV | Target Risk Level (Score) | Target Risk Level (Band) | Target Weight Band | Target Weighted Score | Target Driving Impact Category | Target Driving Impact Level | Inherent Driving Impact Category | Inherent Driving Impact Level | Attributes | Aggregate Costs | Associations | Handling Strategy Cost ($) | Handling Strategy Duration (Days) | Custom List 1 | Custom List 2 | Custom Date 1 | Title | ID | Plan Owner | Strategy | High Level Description | Fallback Plan Description | Planned Start | Planned Completion | Plan Status
Contractual Assumptions |  | Ward, James A | Draft |  | Undefined |  | Construction | Undefined |  |  | Project Risk | IF contractural assumptions are found to be in error, at anytime during contract execution, | UCEP 020 has multiple large construction subcontracts planned to accomplish UCEP requirements. These include major surface construction, subsurface safety significant crane installation, drilling of a borehole, and others. The subcontracts include 3-4 in the $1.5M to $3M range, one at ~$15M, and two at ~$30M ($27M-$32M). | THEN cost or schedule may be negatively impacted. |  | 20-Aug-2024 |  |  |  |  | Undefined |  |  | Undefined |  |  |  |  | Indication or realization of a condition different than the design and/or contract conditions. | Various 60.04 | A&W-INS-201N A&W-INS-153N A&W-INS-152N A&W-INS-200N10 A&W-INS-190N CW-INS-053N CW-INS-040N AHC-INS-0010 ZRC-INS-0010 NET-1150 NET-1080 VDSU-590 SW-SME-130 SW-SME-110 SW-SME-120 SW-SME-100 SW-CV-00 PINS-390N PINS-430 PINS-315 INV-PMT-3037N A&W-INS-151N PINS-420N20 PINS-420N30 SW-CV-320-2 SW-CV-310 SW-CV-280 SW-CV-300 SW-CV-330 SW-CV-320-3 SW-CV-320 | M1 |  |  |  |  | Nwogbe, Susan O | Undefined | Undefined | Undefined | Undefined | Undefined | Management Reserve |  | Test | Plan for Contractual Assumptions | Undefined | None |  | 1. Enterprise Scoring Scheme |  |  |  |  | Cost | USD | Project Schedule | Days | Mission Performance | [19 empty] | Threat | Triangular | 50 |  |  | 3000000 | 6000000 | 12000000 | 32 | 64 | 128 | 0 | 0 | 0 | [41 empty] | Threat | Triangular | 50 |  |  | 2250000 | 4500000 | 9000000 | 32 | 64 | 128 | 0 | 0 | 0 | [42 empty] | 0 | 7000000 | 3500000 | 20 | High : 20.0 |  |  | 0 | Project Schedule (Days) | Significant:4 | 5250000 | 2625000 | 20 | High : 20.0 |  | 0 | Project Schedule (Days) | Significant:4 | Project Schedule (Days) | Significant:4 |  | False |  | 50000 | 0 | Undefined | Undefined |  | Plan for Contractual Assumptions |  | Undefined | Mitigate (T) | Manage and update interim delivery milestones to keep needed products moving forward. |  | 20-Aug-2024 | 26-Feb-2025 | Undefined